## Sheet1
Task/Activity |  | Doc/Component
What | 'Check in' | Where | When | Who | How Long (hours) | Notes
Cull Requirements from Notes | Draft A | GP Requirements doc | 2013-09-20 | Susan | 2.5
Cull Requirements from Notes | Draft B | GP Requirements doc | 2013-10-15 | Susan | 2
GP Task Flowchart | Draft A | GP Task Flow.vsd | 2013-10-15 | Susan | 0.5
Meeting on Requirements | email note |  | 2013-10-15 | S,F,R,J | 1
Arch Diagramming | Several initial drafts | VSDs + their PDFs | 2013-10-22 | Susan | 2.5
Meeting of REquirements and program flow |  |  | 2013-10-18 | S,U,L | 0.75
High Level Design for Project Plan |  | Data Flow Diagram.vsd | 2013-10-24 | Susan | 1.5
High Level Design for Project Plan |  | Data Dictionary.vsd | 2013-10-24 | Susan | 2.5
High Level Design for Project Plan |  | System Class Diagram.vsd | 2013-10-25 | Susan | 1
Update Project Plan with diagrams |  | Project Plan.gdoc | 2013-10-25 | Susan | 0.5
Create SRS document to attach to project plan |  | SRS GP Genie.docx | 2013-10-25 | Susan | 2 | Removed the diagrams and requirements from project plan to an SRTS doc to be used later for requirements trraceability.
Problem Description for GP |  | Problem Description .doc | 2013-10-23 | Li | 0.5
Problem Description for GP |  | Problem Description .doc | 2013-10-24 | Li | 1.5
Team meeting on program design |  |  | 2013-10-29 | U,L,J,R,S | 1 | Team review of the tree traversal method, detailed logic for random tree building, setting development priorities
Diagramming (attempts - no check-in) |  |  | 2013-11-02 | Susan | 2 | Trying to capture the tree-building logic in FSD; stuck.
Team meeting to review Li's coding progress |  | TreeNode class? | 2013-11-05 | L,F,R,S | 0.7
Team meeting to review code issues, source repository |  | NA | 2013-11-12 | L,R, U S | 1.5 | Worked through ideas for noting depth level of gen'd nodes Selected GitHub and created user accounts
Work on project Plan | Rev A | name of doc | 2013-10-24 | Felista
Work on roles, project process | Revs A | names of docs | 2013-10-24 | Justin
work on Traceability matrix | Rev A | name of doc | 2013-10-25 | Roger
Investigation of Source Repos |  |  | 2013-11-13 | Roger
Code: Algorithm Proof of Concept |  | name the source modules one line per work session per module | 10/26 - 11/13 | Li
Set up source & doc repository |  | GitHub | 2013-11-13 | Susan | 1 | Docs from google drive to repos directory
Checked src into GitHub | (commit ID?) | all | 2013-12-02 | Susan | 0.5 | from the zip Li sent on Mon 25th
Added "0" to operands | (commit ID?) | GPTree.java | 2013-12-02 | Susan | 0.1 | recalled from team meeting; did not test
checked in clean ProjectPlan | (commit ID?) | ProjectPlan.docx | 2013-12-02 | Susan | 0.1 | from email Oct 25
added new prost-project analysis | (commit ID?) |  | 2013-12-02 | Susan | 0.1 | from Justin
added assgn 10 | (commit ID?) | SWAssign1-_Sat_13F | 2013-12-02 | Susan | 0.1 | from Roger
Req Change Analysis |  | PCR-1 Requirement Change Action.txt | 2013-12-02 | Susan | 0.5
Save requirements change request to project |  | Requirement Change to Git | 2013-12-02 | Susan | 0.1
Req Change Analysis - training data analysis |  | Req Change Analysis with Training Data.xlsx | 2013-12-02 | Susan | 0.75