## Sheet1
Task/Activity |  | Doc/Component
What | 'Check in' | Where | When | Who | How Long (hours) | Notes
Cull Requirements from Notes | Draft A | GP Requirements doc | 2013-09-20 | Susan | 2.5
Cull Requirements from Notes | Draft B | GP Requirements doc | 2013-10-15 | Susan | 2
GP Task Flowchart | Draft A | GP Task Flow.vsd | 2013-10-15 | Susan | 0.5
Meeting on Requirements | email note |  | 2013-10-15 | S,F,R,J | 1
Arch Diagramming | Several initial drafts | VSDs + their PDFs | 2013-10-22 | Susan | 2.5
Meeting of REquirements and program flow |  |  | 2013-10-18 | S,U,L | 0.75
Project Plan - Schedule and Roles |  | Project Plan - Work Plan | 2013-10-23 | Ujin | 1
High Level Design for Project Plan |  | Data Flow Diagram.vsd | 2013-10-24 | Susan | 1.5
High Level Design for Project Plan |  | Data Dictionary.vsd | 2013-10-24 | Susan | 2.5
High Level Design for Project Plan |  | System Class Diagram.vsd | 2013-10-25 | Susan | 1
Update Project Plan with diagrams |  | Project Plan.gdoc | 2013-10-25 | Susan | 0.5
Create SRS document to attach to project plan |  | SRS GP Genie.docx | 2013-10-25 | Susan | 2 | Removed the diagrams and requirements from project plan to an SRTS doc to be used later for requirements trraceability.
Problem Description for GP |  | Problem Description .doc | 2013-10-23 | Li | 0.5
Problem Description for GP |  | Problem Description .doc | 2013-10-24 | Li | 1.5
Team meeting on program design |  |  | 2013-10-29 | U,L,J,R,S | 1 | Team review of the tree traversal method, detailed logic for random tree building, setting development priorities
Diagramming (attempts - no check-in) |  |  | 2013-11-02 | Susan | 2 | Trying to capture the tree-building logic in FSD; stuck.
Team meeting to review Li's coding progress |  | TreeNode class? | 2013-11-05 | L,F,R,S | 0.7
Team meeting to review code issues, source repository |  | NA | 2013-11-12 | L,R, U S | 1.5 | Worked through ideas for noting depth level of gen'd nodes Selected GitHub and created user accounts
Work on project Plan | Rev A | name of doc | 2013-10-24 | Felista
Work on roles, project process | Revs A | names of docs | 2013-10-24 | Justin
work on Traceability matrix | Rev A | name of doc | 2013-10-25 | Roger
Investigation of Source Repos |  |  | 2013-11-13 | Roger
Code: Algorithm Proof of Concept |  | name the source modules one line per work session per module | 10/26 - 11/13 | Li
Set up source & doc repository |  | GitHub | 2013-11-13 | Susan | 1 | Docs from google drive to repos directory
Checked src into GitHub | (commit ID?) | all | 2013-12-02 | Susan | 0.5 | from the zip Li sent on Mon 25th
Added "0" to operands | (commit ID?) | GPTree.java | 2013-12-02 | Susan | 0.1 | recalled from team meeting; did not test
checked in clean ProjectPlan | (commit ID?) | ProjectPlan.docx | 2013-12-02 | Susan | 0.1 | from email Oct 25
added new prost-project analysis | (commit ID?) |  | 2013-12-02 | Susan | 0.1 | from Justin
added assgn 10 | (commit ID?) | SWAssign1-_Sat_13F | 2013-12-02 | Susan | 0.1 | from Roger
Req Change Analysis |  | PCR-1 Requirement Change Action.txt | 2013-12-02 | Susan | 0.5
Save requirements change request to project |  | Requirement Change to Git | 2013-12-02 | Susan | 0.1
Req Change Analysis - training data analysis |  | Req Change Analysis with Training Data.xlsx | 2013-12-02 | Susan | 0.75
Added test case reference | CID e5f342d | Tracebility matrix | 2013-12-02 | Roger | 0.5
Added cell # and assn 10 | CID 5d2f5d9 | Phone # and doc | 2013-12-02 | Roger | 2
Updated assn 10 | CID 8c3aed0 | document | 2013-12-03 | Roger | 0.25
Added test case design | CID 5s70281 | Test case design.xls | 2013-12-03 | Roger | 1
Revised test case design | CID d7aa179 | Document revision | 2013-12-05 | Roger | 0.75
Working Meeting |  | Code, Test, PPT, Report content | 2013-12-06 | R, U, S, F, L | 4
Proposed change mangement diagram | CID 8d4e101 | Change mangement.ppt | 2013-12-07 | Roger | 0.75
Proposed assignment 10 .ppt | CID 317401e | Assn 10 .ppt | 2013-12-07 | Roger | 1
Updated assn 10 and traceability matrix | CID 237a8c4 | Revised existing docs | 2013-12-07 | Roger | 2 | In care of Susan
Working online meeting - code work |  | Review of code, walkthroughs for code reviews | 2013-12-07 | L, S | 1
Created RSC spreadsheet for GP Genie | CID 870b9d0 | SW measurement tool | 2013-12-08 | Roger | 2
Working Meeting on site |  | Review of code, report,project needs | 2013-12-09 | U, L, S, R, F, J | 2
Early code familiarity and review |  | Working through each module, early output investigation | 2013-12-09 | Susan | 3
Added SCM content to final paper | CID d57c74e | Final paper | 2013-12-12 | Roger | 0.75
Updated test case results | CID 2917998 | Test case design.xls | 2013-12-12 | Roger | 0.75
analysis and solving readable tree format | CID 8c5b78b | Java code; | 2013-12-12 | Susan | 2
functional test runs and captures for test plan scripts | CID 4ea9f4f | FunctionalTestRunsFitness.xlsx | 2013-12-13 | Susan | 3
analysis of usable print test results in fitness evaluator spreadsheets | CID b0f3d7f | CodeTestingEarlyAnalysis.xlsx | 2013-12-12 | Susan | 2
check in mutation update from Li | CID 95d0b09 | mutation.java | 2013-12-13 | Susan | 0.1
final design doc & add to report | CID 37c8bc1 | Final Class Diagram visio, report | 2013-12-13 | Susan | 1.5
code merge correction | CID d61fbe1 | Code check-in collision | 2013-12-13 | Susan | 1
test run: functional testing to analyse bad fitness values | CID 72e7c66 | FuncitnalTestRunsFitness.xlsx | 2013-12-13 | Susan | 1
analysis and review of the fitness output defect | NA | Ongoing - Li and Susan together | 2013-12-13 | Li & Susan | 1
Team Meeting | NA | Updated report, slides, code | 2013-12-13 | U, L, R, F, J, S | 2
Slide development | emailed | final preso to Ujin | 2013-12-14 | Susan | 1
Code testing for fitness; test results updates | CID 82fd6a9 | Test Captures | 2013-12-14 | Susan | 0.5
User testing for valid, invalid data entry | CID b98994c | Test Captures | 2013-12-14 | Susan | 0.5
Project Final Report | Final Report.doc | GitHub | 2013-12-13 | Ujin | 5
Project PPT | Project PPT | GitHub | 2013-12-14 | Ujin | 3